## Sheet1
S/N | API | MODULE | DESCRIPTION | AUTHOR | STATUS (PENDING / CREATED / TESTING / REVISION / VERIFIED) | Test Cases | Revision Remarks | Avg. API Response Time
1 | register | authentication | Creates an account on the platform for the user | Russell J Emekoba | REVISION | sucessful registration failed registration due to expected fields not provided Status codes | Registration failed due to a new user HttpException Throws 501 |  | Solve
2 | verify otp | notification | Receives the otp from the user to confirm their number/email is valid | Russell J Emekoba | TESTING
3 | login | authentication | Starts an active session for a user | Russell J Emekoba | VERIFIED | Verify Login with expected fields Verify Login status code Verify Login Response body Verify Login Request body | Login Successful, Status code =201(Created) |  | Solve
4 | get countries | utilities | Gets a list of all supported countries for the client to choose from during registration | Russell J Emekoba | REVISION | Verify response message and body Verify the status code Verify Pagination | Status code 404 Url can't be found |  | Solve
5 | forgot password | authentication | Initiates password restoration for the user by sending them an email with a reset pin | Russell J Emekoba | REVISION | Verify email is sent Verify status code Verify the response message verify error message if wrong email is put | On sucess, status code should be successful(Ok 200) not 201 On wrong email. statuc code should be 404, 400 not 501 plus the response message should be `User(user email) doesn't exist` |  | Solve
6 | send firebase notification | notification | Send notificaton via firebase cloud messaging | --- | TESTING
7 | reset password | authentication | Changes the users forgotten password with the new password | Russell J Emekoba | VERIFIED | Verify password is reset successfully Verify password set is right passwword verify status code Verify Response Message | Reset password sucessful status code 201 on a wrong email,, status code should be 404, 400 and not 501 |  | Solve
8 | get devices | utilities | Get list and respective ids of all supported devices so that the registrants device is logged | Russell J Emekoba | VERIFIED | Verify status code Verify devices are fetched Verify response body | Status code 201 Message Should be Devcies successfully fetched not Fetched devices successfully |  | Solve
9 | update parent profile | authentication | Allows parent to change their name, profile picture etc | Ganesh Suthar | REVISION |  | The Endpoint doesnt exit on the postman collection
10 | get all users | admin | Allows a user admin to get a list of all users on the platform. They can sort users by region, registration date, grade etc | Ganesh Suthar | VERIFIED | Verify users are returned successfully Verify status code Verify response body | Users successfully returned Status code is right 200
11 | send verifiation code | notification | Sends an OTP to the users number/email | Russell J Emekoba | CREATED
12 | get classes | utilities | Gets a list of all classes for the user to select from | Russell J Emekoba | TESTING
13 | send mail | notification | Sends Notifications via email | Russell J Emekoba | TESTING
14 | find tests | content | allows users to search for a particular test | Ganesh Suthar | CREATED
15 | find test by id | content | allows users to select a test to take by querying for more info (qestions/options/answers) via its id | Ganesh Suthar | CREATED
16 | find test by title | search | allows a user to select a test by its title | --- | CREATED
17 | search students by teacher | search | allows a user to search for students by the teachers id | --- | CREATED
18 | search subjects | search | allows user to search for a subject | --- | TESTING
19 | subscribe to plan | subscription | aloows a user to subscribe to a payment plan | --- | TESTING
20 | on subscription expiry imminent | subscription | notifies a user when their subscription is about to expire | --- | CREATED
21 | resubscribe | subscription | automatically renews a user subscription on expiry | --- | TESTING
22 | suspend user | admin | allows a user to block any user on the platform. The admin must specify their "reason" which is logged alongside the protocol | Ganesh Suthar | CREATED
23 | get subscription plans | subscription | provides the user with a detailed list of all subscription plans on the platform. This will change depending on the registrants region | Ganesh Suthar | CREATED
24 | user bulk upload | admin | allows a user admin to register users on bulk by submitting an excel file with the users' details | --- | CREATED
25 | payment notification | notification | notifies a user that their payment is successful along with a receipt of payment | --- | CREATED
26 | send notification to topic | notification | sends push notifications to all users who subscribed to a specific topic | --- | CREATED
27 | subscribe to topic | notification | allows users to subscribe to push notifications for a topic | --- | CREATED
28 | send to topic | notification | Send notificaton via firebase cloud messaging to all users subscribed to the topic group | --- | CREATED
29 | unsubscribe from topic | notification | removes the user from a topic group so as to stop them from receiving push notifications on that topic | --- | CREATED
30 | get states | utilities | provides a list of supported states based on the country id selected | Russell J Emekoba | CREATED
31 | get countries | utilities | provides a list of supported countries for the user to pick from | Russell J Emekoba | CREATED
32 | get microservices | utilities | provides a list of all active microservices and their respective endpoints | --- | CREATED
33 | create subject | subject | provides a user to create a subject | Ganesh Suthar | CREATED
34 | update subject | admin | allows a user to update details of an already created subject | Ganesh Suthar | CREATED
35 | get all subjects | content | allows a user to get all subjects created | Ganesh Suthar | CREATED
36 | get subject by id | content | allows a user to get details of a single subject by its id | Ganesh Suthar | CREATED
37 | get chapters | content | allows a user to get all chapters for a particular subject id provided | Ganesh Suthar | CREATED
38 | get all user sessions | authentication | allows users and customer care to track a users sessions and devices | Ganesh Suthar | CREATED
39 | end user session | authentication | logs the usre out of the applciation | Ganesh Suthar | CREATED
40 | refresh user session | authentication | allows a user to recover a session | Ganesh Suthar | CREATED
41 | start lesson | admin | allows a teacher to start streaming lessons | --- | PENDING
42 | stop lesson | class | allows a user to leave a lesson | --- | PENDING
43 | join lesson | class | allows a user to join a lesson | --- | PENDING
44 | start interactive mode | class | allows a student to answer live questions from the teacher | --- | PENDING
45 | end interactive mode | class | allows a student to end interactive mode | --- | PENDING
46 | get report card | report card | fetches a students report card | Ganesh Suthar | CREATED
47 | get child metrics | parent console | fetches a students analytics |  | PENDING
48 | get leaderboard data | leaderboard | fetches the leaderboards with their categories (state, country etc) | Ganesh Suthar | CREATED
49 | get user leaderboard details | leaderboard | get details for a single leaderboard entry | Ganesh Suthar | CREATED
50 | update settings | settings | updates a users settings | --- | PENDING
51 | get lesson reviews | content | gets reviews for a particular lesson | --- | PENDING
52 | review lesson | content | allows users to leave a review after a lesson | Ganesh Suthar | PENDING
53 | get lesson transcript | content | fetches transcript for a lesson | --- | PENDING
54 | get lesson video | content | fetches video for lesson | --- | PENDING
55 | get lesson ebook | content | fetches ebooks for lesson | --- | PENDING
56 | get test | content | fetches test for lesson | Ganesh Suthar | CREATED
57 | get upcoming classes | classroom | fetches list for upcoming classes | Ganesh Suthar | CREATED
58 | add child to parent | authentication | adds children to list for parent | Russell J Emekoba | CREATED
59 | get mock tests | mocks | get list of available mock tests and exams | Ganesh Suthar | CREATED
60 | get mock subjects | mocks | get list of subjects with available mock tests. | --- | PENDING
61 | get settings | settings | gets a users settings | Russell J Emekoba | CREATED
62 | get badges | user | gets badges attached to student | Ganesh Suthar | CREATED
63 | upgrade subscription | subscription | allows users to upgrade their subscriptions | --- | PENDING
64 | seed countries | utility | creates default countries | Russell J Emekoba | PENDING
65 | seed devices | utility | creates default devices | Russell J Emekoba | CREATED
66 | get subscription history | admin | allows an admin to generate a list of past subscriptions | Ganesh Suthar | CREATED
67 | get test by chapter | content | allows a user to get a test based on their current chapter | Russell J Emekoba | CREATED
68 | cancel subscription | subscription | allows a user to cancel their subscription | Russell J Emekoba | CREATED
69 | book class | class | allows a user to subscribe to a one time notification for when class starts | --- | PENDING
70 | logout | authentication | allows a user to logout from all sessions on all devices | Ganesh Suthar | REVISION | Verify user is logged out Verify logout status code Verify response body | Api returns 501, Internal server error
72 | create admin | admin | allows a superadmin to create another admin | Ganesh Suthar | CREATED
73 | create customer care agent (cca) | admin | allows an admin to create a customer care agent | Ganesh Suthar | CREATED
74 | update student profile | authentication | allows a parent to update their childs details | Ganesh Suthar | CREATED
75 | update admin profile | admin | allows an admin to update their profile | Ganesh Suthar | CREATED
76 | Get Learning Packages | Utility | allows a user to fetch all the learning packages currently offered by the platform | Russell J Emekoba | CREATED
77 | Create Badge | admin | allows an admin to create a new badge | Ganesh Suthar | CREATED
78 | assign badge to student | gamification | assigns a new badge to a student |  | PENDING
79 | social login | authentication | Allows a user to register | Russell J Emekoba | PENDING
80 | get badge list | content | allows a user to see all existing badges | Ganesh Suthar | CREATED
81 | update mock test | admin | allows an admin to update the values of a mock test | Ganesh Suthar | CREATED
82 | delete mock test | admin | allows an admin to delete a mock test |  | PENDING
83 | create lesson transcript | admin | allows an admin to create and save a transcript for a a video lesson |  | PENDING
84 | update lesson transcript | admin | allows an admin to edit video transcripts |  | PENDING
85 | delete lesson transcript | admin | allows an admin to delete video transcripts |  | PENDING